Fairtrade Action Plan 2024-2026

This Action Plan is updated regularly, which details the specific targets, actions and progress of the Fairtrade endeavours at the University of St Andrews and therefore supplements our Fairtrade Policy.

| Updated on: | Updated by: |
| --- | --- |
| 30/01/26 | Sustainability Coordinator 2025/6 |
| 18/9/25 | Sustainability Coordinator 2025/6 |

| 1. Commitment: Leadership and Strategy |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Objective (Yellow background = Mandatory. White background = optional) | Responsibility |  | Target Date | Progress |  | Status |
| S: The Steering Group that meets regularly and formally leads on efforts to attain, or retain, Fairtrade University and College Award status. M: Minutes from each meeting will be kept including a record of who attended. A: This is relevant to helping us achieve our Fairtrade policy and Mandatory criteria for award - MN004 in toolkit (5 Points) R: The Sustainability Coordinator will ensure that the meeting occurs and minutes are kept. T: The meeting will occur on a quarterly basis. | Steering Committee/Sustainability Coordinator |  | Twice per semester | Need to ensure that meetings keep occurring on a regular basis. |  | Ongoing |
| S: The partnership has a SMART action plan on Fairtrade and has published it. It should include procurement and catering, campaigning and influencing, engagement and communications and a strong focus on the monitoring and evaluation of all activities M: Published online A: Mandatory criteria for award: MN002 on toolkit R: Already have an action plan (this document) just needs to be published T: By March 2026 | Sustainability Coordinator |  | March 2026 | Needs to be re-published on the University’s Sustainability Website. |  | Ongoing |
| S: The partnership has published a public commitment of intent to support and champion Fairtrade and its values within the last two years signed by senior management across the organisations and their retail and catering outlets. M: Having this document published online. A: Mandatory criteria for award - MN003 in toolkit (10 Points) R: There is already a document which requires resigning from appropriate staff in RBS, Estates, Procurement, and the Principal’s Office. T: Current plan runs to March 2026 |  |  | February 2026 | All signatories have resigned the updated policy. Republished on Sustainability Website. |  | Completed |
| S: The union has one or more active policy which supports Fairtrade passed within the last three years and has published them. M: If the document is completed and published A: Optional Criteria for award – LD001 in toolkit (10 points) R: There is a document completed and signed in Summer 2018. T: Needs to be updated and published by March 2026 | President of Union Affairs (Students’ Association) |  | February 2026 | Union is included in the updated policy. |  | Completed |
| S: Within the last two years the partnership has analysed the inclusion of Fairtrade, trade justice and ethical consumption within other cross-cutting institutional and union plans (e.g.: procurement plan, sustainability plan, marketing plan) and made suggestions to the relevant stakeholders of how it could be integrated. M: A document that maps the inclusion of Fairtrade, trade justice and ethical consumption in University policies and possible gaps; a list of stakeholders that have been engaged; any resulting changes to policy A: Optional Criteria for award – LD003 in toolkit (10 points) R: Sustainability Coordinator’s workload but will need support from other members of the Steering Committee T: March 2026 | Sustainability Coordinator/Steering Committee |  | March 2026 | Document confirmed by Sarah Cutler, Procurement Mapping document created Jan 2026. |  | Completed |
| S: There is active leadership on Fairtrade, trade justice and ethical consumption issues from one or more senior members of staff or sabbatical officers in the union and institution. M: Actively supporting a Fairtrade campaign or organising Fairtrade related events A: Optional Criteria for award – LD005 in toolkit (15 points) R: Can get support from other members of the Steering Committee T: On a quarterly basis | President of the Students Association |  | On a quarterly basis | Potential University and Union/Exec support for scoping survey campaign (Jan 2026). |  | Completed |
| 2. Commitment: Campaigning, Influencing and Innovative Interventions |  |  |  |  |  |  |
| Objective/Action | Responsibility |  | Target Date | Progress |  | Status |
| S: The partnership has held a series of events/promotions/engagement activities during Fairtrade Fortnight/Green Week and Sustainability Week and has measured impact across the events. M: Number of people engaged in person; Social media reach A: Mandatory criteria for award - MN004 in toolkit (10 Points) R: T: For the two weeks during Fairtrade Fortnight | Sustainability Coordinator |  | During Green Week (February) and Sustainability Week (March) 2026 | Valentines Day 2025 and 2026, chocolate (bake) sale with The Tree Fairtrade represented at Green Week and four Sustainability Week events. |  | Ongoing |
| S: The partnership has devised and successfully delivered one or more innovative campaigns on Fairtrade, trade justice or ethical consumption in the last year, which have been run in partnership with students. The campaign/s must have taken place in addition to Fairtrade Fortnight and can demonstrate some measures of impact. M: Number of people engaged in person; Social media reach A: Mandatory criteria for award - MN005 in toolkit (15 Points) R: Should try to intertwine into other events to increase engagement and interest. T: Before April 2026 | Sustainability Coordinator/President of Union Affairs (Students’ Association) |  | Before April 2026 | Green week campaign: embedded in two events in the week coupled with social media posts focussing on both global and local fair trade. |  | Ongoing |
| S: The partnership has included Fairtrade and ethical consumption in staff and/or student inductions. These inductions should state the organisation's commitment to Fairtrade, provide some information on why Fairtrade is important, and state some simple actions staff and students can take to fit in with the organisation's values. M: Number of staff who attend the New Staff Essentials; Number of staff who mention Fairtrade in their feedback form from the event. A: Optional Criteria for award – CI001 in toolkit (10 points) R: The presentation is already given and includes Fairtrade. In the updated version of the presentation the Environment Team will ensure to include Fairtrade. T: Whenever a New Staff Essentials occurs, around once every six weeks | Environment Team |  | Whenever an Induction for All New Staff occurs, around once every six weeks | The presentation is already given on a regular basis and includes Fairtrade. Present in student TESA Staff TESA being published in Spring 2026 with Fairtrade section. |  | Ongoing |
| S: The partnership has supported one or more student groups to campaign on Fairtrade, ethical consumption or trade justice. M: Number of students who engage with the Steering Committee; the amount of time the Steering Committee spends supporting the student campaign. A: Optional Criteria for award – CI002 in toolkit (5 points) R: Environment Network (Students’ Association). The President of Union Affairs and the Sustainability Coordinator may have to push significantly in the beginning to get traction with the students in terms of awareness/engagement T: Before April 2026 | Sustainability Coordinator/ President of the Students Association |  | April 2026 | Collaborated with the student cooperative The Tree, Environment subcommittee. |  | Ongoing |
| S: Within the last 2 years the partnership has partnered with a local school or college and worked together on at least one project or campaign over the year. M: Number of events that have occurred with schools; the number of hours that have gone into planning the event/completing the project. A: Optional Criteria for award – CI003 in toolkit (10 points) R: Should be possible, especially working with the Fairtrade Town St Andrews Group T: Before April 2026 | Sustainability Coordinator/Steering Committee/Fairtrade Town St Andrews Group |  | Before April 2026 | Previous Sustainability Coordinator worked with local Fife schools to create a module run by the Student Environment team. Work undertaken to establish relationship with SET and local schools – to be completed after April 2026 |  | Review |
| S: The partnership's work and support of Fairtrade has an effective and up to date web presence, which is easily found and well-used. M: Number of times the website is updated in a year. A: Optional Criteria for award – CI007 in toolkit (5 points) R: It would be useful if the Steering Committee could help provide content to be shared on the website, ie. Updates, interesting information, etc T: On a quarterly basis or more as needed | Sustainability Coordinator/Steering Committee |  | On a quarterly basis or more as needed | Blog on Sustainability website regularly updated |  | Ongoing |
| S: The partnership has utilised social media and other communication channels to communicate Fairtrade campaigns widely and successfully M: Number of posts made in a month; Number of people who are reached or engage with the posts A:Optional Criteria for award – CI008 in toolkit (5 points) R: It would be useful if the Steering Committee could help provide content to be shared on social media, ie. Updates, interesting information, ect T: On a bi-monthly basis | Sustainability Coordinator |  | On a bi-monthly basis | University of St Andrews social media platforms e.g. Instagram, Facebook, MS Teams channel. This is already part of the Sustainability Coordinator’s role |  | Ongoing |
| S: The partnership ensures there is a strong Fairtrade presence at Fresher's Fayres (or equivalent) and/or recruitment days. M: - Number of students engaged at Fresher's Fairs (or equivalent); Number of events a representative of the Fairtrade Steering Committee attends A: Optional Criteria for award – CI010 in toolkit (10 points) R: Will hopefully engage people in Fairtrade T: At least three times a year at the Fresher’s Fayre, Refresher’s Fayre, and the Charities Fayre. | Sustainability Coordinator |  | At least three times a year at the Fresher’s Fayre, Refresher’s Fayre, and Green Week/Sustainability Fayres. | This is already a part of the Sustainability Coordinator’s role. |  | Completed |
| 3. Commitment: Procurement, Retail, and Catering |  |  |  |  |  |  |
| Objective/Action | Responsibility |  | Target Date | Progress |  | Status |
| S: Any retail or catering outlets owned/operated by the partnership stock Fairtrade certified products in the following categories and are working to increase either the number of lines OR number of items sold year on year: Tea; Coffee; Sugar; Hot Chocolate and cocoa; Chocolate, confectionary or snacks; Cotton Clothing M: Using purchasing and sales records A: Mandatory criteria for award - MN006 in toolkit (10 Points) R: T: To be achieved by January 2026 | RBS |  | January 2026 | Currently selling Fairtrade Food in all University cafes, restaurants and bars. Fairtrade clothing items being sold in university shop. |  | Ongoing |
| S: Any retail, catering or other commercial outlets owned or operated by the partnership stock at least one Fairtrade certified line in at least 2 of the following categories (where the category is stocked): soft drinks; wine or beer; health and beauty; savoury snacks and nuts; cut flowers; fruit M: Using purchasing records A: Mandatory criteria for award - MN007 in toolkit (10 Points) R: T: To be achieved by January 2026 | RBS |  | January 2026 | Currently selling Fairtrade bananas. Fairtrade juice sold in retail. Fairtrade tea/coffee sold in retail, commercial catering and Students Association. Fairtrade wine sold in Students Association bar. |  | Complete |
| S: Have up to date and regularly changed Point Of Sale (POS) material in all relevant outlets, highlighting Fairtrade products and providing information on the benefits of Fairtrade to growing communities. M: Record the number of posters/table talkers that are visible in cafes and catering areas. A: Mandatory criteria for award - MN008 in toolkit (10 Points) R: Can ask the Fairtrade Foundation for more POS items or make our own. T: To be achieved by March 2025 | RBS/ Sustainability Coordinator |  | March 2026 | New flyers up in WBH and at coffee stations. |  | Completed |
| S: The partnership has proactively engaged staff and publicised Fairtrade widely as an alternative to communal tea, coffee, hot chocolate and sugar in staff areas and offices. M: Using procurement records and email records A: Optional Criteria for award – PL001 in toolkit (5 points) R: Will be difficult to convince staff to change the type of coffee they buy. Could try to convince them by having a coffee taste test morning and an effective advertising campaign T: To be achieved by March 2026 | Procurement/ RBS/ Sustainability Coordinator |  | March 2026 | Focus on Walter Bower house at Eden Campus. Estates bulletin, ITL, and social media |  | Ongoing |
| S:The partnership's catering providers and licenced premises (internal and/or contracted) offer Fairtrade certified products as standard in all the following categories (where stocked): • Fruit • Juice • Tea • Coffee • Sugar • Chocolate • Wine M: Using procurement records A: Optional Criteria for award – PL002 in toolkit (10 points) R: T: | RBS |  | March 2026 | Confirmed by DL |  | Ongoing |
| S: The partnership has captured Fairtrade sales data for the previous two academic years and reported back to the Fairtrade Foundation.. M: Number of sales A: Optional Criteria for award – PL003 in toolkit (15 points) R: T: Upload by March 26 | Procurement/ RBS |  | March 2026 | Confirmed by DL |  | Ongoing |
| S: The partnership has included terms in tender documentation that reference Fairtrade requirements for relevant categories, or states that Fairtrade suppliers will be preferred. M: Evidence of Fairtrade in tender/procurement documentation A: Optional Criteria for award – PL005 in toolkit (5 points) R: T: | RBS/ Procurement |  | October 2025 | Procurement policy and action plan |  | Completed |
| S: EITHER Fairtrade is served as standard in hospitality (e.g. conferences, vacation hotel rooms etc.) across all products which have a Fairtrade option available - tea, coffee, sugar etc., OR within the last two years demonstrable progress has been made to put this into practice M: Sales data, delivered catering menu, Fairtrade lines available for customers to purchase A: Optional Criteria for award – PL006 in toolkit (10 points) R: T: | RBS |  | Continue doing | Yes, this is still the case |  | Completed |
| S: Sales promotions (such as discounts, competitions, loyalty cards etc.) are run on Fairtrade certified products periodically throughout the year, across relevant retail outlets. M: Evidence of promotions in internal/external communications A: Optional Criteria for award – PL010 in toolkit (5 points) R: T: | RBS |  | September 2025 | Sustainability Coordinator and Environment Network hosted a Fairtrade bubble tea pop-up promotional stall (October 2025). Fairtrade Survey voucher promotion (February 2026) – 227 respondents, 3 voucher winners. |  | Completed |
| S: The partnership can demonstrate an increase in the number of Fairtrade certified items and/or lines bought for sale in campus commercial outlets over the last two years. M: Sales data, Fairtrade lines available to purchase A: Optional Criteria for award – PL011 in toolkit (15 points) R: T: | RBS |  | March 2026 | University Shop increased Fairtrade cotton range sales 2024 to 2025 |  | Ongoing |
| 4. Commitment: Research and Curriculum |  |  |  |  |  |  |  |  |  |
| Objective/Action | Responsibility |  | Target Date | Progress | Status |  |
| S: Within the last two years the partnership has successfully carried out a relevant follow-up research/scoping exercise amongst a broad range of its students and staff to inform its Fairtrade work, and has made the findings publicly available. M: Analysis of survey responses A: Mandatory criteria for award - MN009 in toolkit (5 Points) R: T: Feb 2026 | Sustainability Coordinator |  | March 2026 | SC produced, published and promoted Fairtrade Survey in Feb 2026 in conjunction with University cafe voucher competition. Results and analysis published on Sustainability blog | Completed |  |
| S: The partnership provides and publicises opportunities for students to investigate Fairtrade, trade justice or ethical consumption issues on or off-campus within their course work or dissertations. M: A: Mandatory criteria for award - MN010 in toolkit (5 Points) R: T: | Steering Committee/Sustainability in the Curriculum Committee Mary from Town Group liaise with JTS |  | March 2025 | Transition have added some ideas to living labs webpage Check on this and update | Ongoing |  |
| 5. Commitment: Outcomes |  |  |  |  |  |  |
| Objection/Action | Responsibility | Target Date | Progress |  |  | Status |
| S: The Steering Group publishes an annual progress or impact report on its action on Fairtrade, trade justice and ethical consumption. This should refer to the tasks and progress made through the SMART action plan and should be publicly available. M: Through the published report A: Mandatory criteria for award - MN011 in toolkit (10 Points) R: T: Published in July/August annually | Steering Committee/ Sustainability Coordinator | Summer of every year | Reports to be written in July/August for each academic year. Fairtrade is mentioned within Public Bodies Climate Change Duty report 2024 and 2025. Get recognised in Annual Sustainability Report |  |  | Ongoing |
| S: The partnership has identified positive outcomes for students through its Fairtrade work. Outcomes are things like greater awareness, a change in attitudes, new skills, learning, increased confidence, new friendships, being more employable, increased Fairtrade purchasing rates, higher meaningful attendance at Fairtrade events and campaigns, increased lines of Fairtrade products available to students. (Don’t confuse outcomes with outputs. Outputs are what generate the outcomes, such as surveys, toolkits, events, engagement, webpages and media coverage) M: survey questions – a mix of qualitative and quantitative examples A: Optional criteria for award – OT001 in toolkit (20 Points) R: T: | Steering Committee/ Sustainability Coordinator | March 2025 | We have quantitative evidence of increased attendance and Fairtrade purchasing rates, and qualitative evidence of student quotes from events. Some of Feb 2026 Fairtrade Survey answers showed meaningful engagement with Fairtrade. |  |  | Ongoing |
| S: As above, but identifying positive outcomes for student’s association M: survey questions? – a mix of qualitative and quantitative examples A: Optional criteria for award – OT002 in toolkit (20 Points) R: T: |  | March 2026 | Discuss groups associated with the SA - UN Women, Env Network… Will update with new survey |  |  | Ongoing |
| S: As above, but identifying positive outcomes for the institution M: survey questions? – a mix of qualitative and quantitative examples A: Optional criteria for award – OT003 in toolkit (20 Points) R: T: |  | March 2026 | Staff surveyed in Fairtrade Survey, some had positive comments and one won voucher. |  |  | Ongoing |
| S: As above, but identifying positive outcomes for the wider community M: survey questions? – a mix of qualitative and quantitative examples A: Optional criteria for award – OT004 in toolkit (20 Points) R: T: |  |  | Can confirm that more students were involved in town group. Towns Group involvement with Fairtrade cotton supplier (Koolskools SUstainable) projects (Sustainability Week, March 2026). |  |  | Ongoing |